## Use Cases
# | Feature | Use case | Guest | Tenant | Landlord | Admin | Use case description
1 | Login | Login |  | x | x | x | Allows users to verify their identity and access registered systems or applications.
2 | Logout | Logout |  | x | x | x | Allows Tenant, Landlord and Admin to log out of the system or application, ending the current session.
3 | Register | Register | x |  |  |  | Allows users to create new personal accounts on the system.
4 | Password Retrievement | Forgot password |  | x | x | x | Allows users to reset their password when they forget their old password
5 | Account management | Change password |  | x | x |  | Allows users to change personal password to enhance account security
6 | Profile management | Update profile |  | x | x |  | Allows users to update public personal information in account information.
7 | Profile management | Upload user avatar |  | x | x |  | Allow tenants and landlords to upload customized avatar
8 | Search post | Search post | x | x | x | x | Allows user to enter search string and other criteria into search box to search for houses
9 | View post list | View post list | x | x | x | x | Allows users to access detailed information and media for rental properties, aiding their decision-making process
10 | View home page | View home page | x | x | x | x | Allows users to access the main interface, providing an overview and access to various features.
11 | View post detail | View house detail | x | x | x | x | Allow users to access comprehensive information, including photos and specs, for a specific rental property.
12 | Rating and review | Vote for post |  | x |  |  | Allows tenants to provide a score rating for their housing experience.
13 | Rating and review | Comment for post |  | x |  |  | Allows tenants to add comments or feedback to a rental property listing.
14 | Wishlist | Add to wishlist |  | x |  |  | Allows tenants to save properties they're interested in to a wishlist for future reference.
15 | Wishlist | View wishlist |  | x |  |  | Allows tenants to view all property they have been added to wishlist, optionally navigate to them or delete from wishlist
16 | Wishlist | Remove from Wishlist |  | x |  |  | Allow tenants to remove a post from their wishlist
17 | Manage tenant's orders | Create an order |  | x |  |  | Allows tenants to initiate the process of renting a property they have selected.
18 | Manage tenant's orders | Cancel an order |  | x |  |  | Allows tenants to remove a rental order they no longer wish to pursue.
19 | Manage tenant's orders | View tenant's orders |  | x |  |  | Allow tenants to review their past rental orders.
20 | Landlord Profile View | View landlord's profile |  | x |  |  | Allows tenants access comprehensive data about landlord when landlord approve their rental order.
21 | System Report | Process report |  |  |  | x | Allows administrators to change status of a reported issues or claims, indicating the issues has been resolved.
22 | System Report | Send report |  | x | x |  | Allows tenants and landlords to document and report issues encountered when using the system, such as user, system, etc.
23 | System Report | View report |  | x | x |  | Allow tenants and landlords to view their reports and their status.
24 | System Report | Cancel report |  | x | x |  | Allow tenants and landlords to cancel their sent reports.
25 | Post management | Publish new post |  |  | x |  | Allows landlord inputs property specifics, adds high-quality images, sets rent details, and publishes a compelling listing for potential tenants to view.
26 | Post management | Update a post |  |  | x |  | Allow landlord selects a rental post to update, edits property information, and saves changes to keep the listing current.
27 | Post management | Remove personal post |  |  | x |  | Allow landlord selects a rental post for removal, confirms deletion, and removes the listing from the platform.
28 | Post management | Hide a post |  |  |  | x | Allows administrators to hide a post, ensuring compliance with guidelines or addressing inappropriate posts
29 | Post management | View all personal posts |  |  | x |  | Allow landlords to view all theirs post in one place.
30 | Post management | Pay for post |  |  | x |  | Allow landlords to make payment for posts.
31 | User account manipulation | Add account |  |  |  | x | Allows administrators to generate a tenant/landlord/admin account.
32 | User account manipulation | Update account |  |  |  | x | Allows administrators to modify account information or permissions for a particular user.
33 | User account manipulation | Disable account |  |  |  | x | Allows administrators to change the active or inactive status of a user account.
34 | User account manipulation | Ban account |  |  |  | x | Allow administrators to ban an account
35 | User account manipulation | Unban account |  |  |  | x | Allow administrators to unban an account
36 | User account manipulation | View all account |  |  |  | x | Allow administrators to view all registered account
37 | Order management | View landlord's orders |  |  | x |  | Allows landlords access a list of pending orders from tenants that require their attention and action.
38 | Order management | Process an order (Approve/Reject) |  |  | x |  | Allows landlords to change the status of a rental order that has been approved.
39 | Point management | Add point to landlord |  |  |  | x | Allows admin to add points to landlord accounts.
40 | Point management | View transaction history |  |  | x |  | Allows landlord to view all their transaction history, including deposit and post payment
41 | Tenant Profile View | View tenant's profile |  |  | x |  | Allows landlord accesses tenant details, including personal information, and contact information.
42 | Promotion management | Update promotion |  |  | x |  | Allow landlord to update a new promotional offer, such as reduced rent or incentives, to attract potential tenants to their rental listing.
43 | Promotion management | Create a promotion |  |  | x |  | Allows landlord initiates a new promotional campaign, specifying details like discounts, incentives, or special offers to attract prospective tenants.
44 | Promotion management | Remove promotion |  |  | x |  | Allows landlord selects an active promotion, confirms removal, and removes it from the rental listing to end the promotional offer.
45 | Promotion management | View promotion |  |  | x |  | Allows landlord to view all active promotions.
46 | Promotion management | Update duration of promotion |  |  | x |  | Allow landlord to update the duration of a promotion item.

## Product
# | Feature | Screen/Function | Screen/Function Details | In Charge | Status | RDS | Planned | Actual | Updated | Update Details
1 | Login | Login | Login function for Tenant, Landlord and Admin - Verify status of Tenant/Landlord. User must verify the email before logging in. If it's unverified account, send confirmation email - Login logic (compare password hash) - Seperate login page for Admin role - Authorization | ThangHQ | Done |  | iter1 | iter1 | iter2 | - Update for check ban account - Update login for Admin account at a seperate page
2 | Logout | Logout | Invalidate server session | ThangHQ | Done |  | iter1 | iter1 | not yet
3 | Create new personal account | Register | Register function for Tenant, Landlord (Admin cannot registered, only added by other Admins) - Check email existence before proceed to register, one email can only correspond to one role. - Send confirmation email - Verify password conforms to password requirements | ThangHQ | Done |  | iter1 | iter1 | not yet
4 | Password Retrievement | Forgot password | Enter email for password recover - For verified account - If there are 2 accounts, unverified, same email on the database | ThangHQ | Done |  | iter1 | iter1 | iter3 | - Handle cases when there are two account with the same email, unverified
5 | Account management | Change password |  | TungDT | Done |  | iter1 | iter1 | not yet
6 | Profile management | Update profile |  | SyTT | Done |  | iter1 | iter1 | not yet
7 | Profile management | Upload user avatar |  | AnhNT | Done |  | iter3 | iter3 | not yet
8 | Search post | Search post | Search function for Guest, Tenant, Landlord and Admin - User search house by KEYWORD, criteria PRICE, AREA, LOCATION, BEDROOMS, TYPE - The system will check the data in the database. If there is data that matches that keyword, it will be displayed on the corresponding house, otherwise nothing will be displayed. | AnhNT | Done |  | iter1 | iter1 | iter3 | Fixing bugs arise when adding pagination
9 | View post list | View post list | View function for Guest, Tenant, Landlord and Admin - The website will display all data about the posts that Landlord have posted and managed | AnhNT | Done |  | iter1 | iter1 | not yet
10 | View home page | View home page | - At the top of the website, the rooms with the highest price (of the best quality) will be displayed to customers - In the middle of the website will be the latest posted and untenured rooms | AnhNT | Done |  | iter1 | iter1 | not yet
11 | View post detail | View house detail | View detail function for Guest, Tenant, Landlord and Admin - When the user clicks on the title name (room name), the website will redirect to a page displaying all detailed data about that room. | AnhNT | Done |  | iter1 | iter1 | not yet
12 | Rating and review | Vote for post |  | KhanhNB | Done |  | iter2 | iter2 | not yet
13 | Rating and review | Comment for post |  | KhanhNB | Done |  | iter2 | iter2 | not yet
14 | Wishlist | Add to wishlist |  | ThangHQ | Done |  | iter2 | iter2 | not yet
15 | Wishlist | View wishlist |  | ThangHQ | Done |  | iter2 | iter2 | not yet
16 | Wishlist | Remove from Wishlist |  | ThangHQ | Done |  | iter2 | iter2 | not yet
17 | Manage tenant's orders | Create an order |  | SyTT | Done |  | iter2 | iter2 | not yet
18 | Manage tenant's orders | Cancel an order |  | KhanhNB | Done |  | iter2 | iter2 | not yet
19 | Manage tenant's orders | View tenant's orders |  | SyTT | Done |  | iter2 | iter2 | not yet
20 | View landlord's profile | View landlord's profile |  | SyTT | Done |  | iter3 | iter3 | not yet
21 | System Report | Process report |  | AnhNT | Done |  | iter3 | iter3 | not yet
22 | System Report | Send report |  | SyTT | Done |  | iter3 | iter3 | not yet
23 | System Report | View report |  | SyTT | Done |  | iter3 | iter3 | not yet
24 | System Report | Cancel report |  | SyTT | Done |  | iter3 | iter3 | not yet
25 | Post management | Publish new post |  | TienPV | Done |  | iter2 | iter2 | not yet
26 | Post management | Update a post |  | TienPV | Done |  | iter2 | iter2 | not yet
27 | Post management | Remove personal post |  | TienPV | Done |  | iter2 | iter2 | not yet
28 | Post management | Hide a post |  | TienPV | Done |  | iter2 | iter2 | not yet
29 | Post management | View all personal posts |  | TienPV | Done |  | iter2 | iter2 | not yet
30 | Post management | Pay for post |  | TienPV | Done |  | iter2 | iter2 | not yet
31 | User account manipulation | Add account |  | TungDT | Done |  | iter2 | iter2 | not yet
32 | User account manipulation | Update account |  | TungDT | Done |  | iter2 | iter2 | not yet
33 | User account manipulation | Disable account |  | TungDT | Done |  | iter2 | iter2 | not yet
34 | User account manipulation | Ban account |  | ThangHQ | Done |  | iter3 | iter3 | not yet
35 | User account manipulation | Unban account |  | ThangHQ | Done |  | iter3 | iter3 | not yet
36 | User account manipulation | View all account |  | TungDT | Done |  | iter2 | iter2 | not yet
37 | Order management | View landlord's orders |  | TienPV | Done |  | iter2 | iter2 | not yet
38 | Order management | Process an order (Approve/Reject) |  | TienPV | Done |  | iter2 | iter2 | not yet
39 | Point management | Add point to landlord |  | ThangHQ | Done |  | iter2 | iter2 | not yet
40 | Point management | View transaction history |  | ThangHQ | Done |  | iter2 | iter2 | not yet
41 | Tenant Profile Access | View tenant's profile |  | TienPV | Done |  | iter2 | iter2 | not yet
42 | Promotion management | Update promotion |  | KhanhNB | Done |  | iter1 | iter1 | not yet
43 | Promotion management | Create a promotion |  | KhanhNB | Done |  | iter1 | iter1 | not yet
44 | Promotion management | Remove promotion |  | KhanhNB | Done |  | iter1 | iter1 | not yet
45 | Promotion management | View promotion |  | KhanhNB | Done |  | iter1 | iter1 | not yet
46 | Promotion management | Update duration of promotion |  | KhanhNB | Done |  | iter2 | iter2 | not yet

## Iter1
# | Screen / Function | In Charge | Status | Notes
1 | Design ERD | SyTT | Done
2 | UC Diagram | TienPV, SyTT | Done
3 | Write SQL Command | AnhNT | Done
4 | Register for Tenant | ThangHQ | Done | Complete basic register logic (encrypt password, add to database). Sending comfirmation email
5 | Login | ThangHQ | Done | Completed login logic for Tenant and Landlord
6 | Logout | ThangHQ | Done | Completed logout
7 | Update personal password | TungDT | Done | Done
8 | Search house by keyword | AnhNT | Done | Done
9 | Search house by price | AnhNT | Done | Done
10 | Search house by area | AnhNT | Done | Done
11 | Search house by location | AnhNT | Done | Done
12 | Search house by number of bedrooms | AnhNT | Done | Done
13 | Search for house by house type | AnhNT | Done | Done
14 | Update new promotion | KhanhNB | Done | Done
15 | Update duration of promotion | KhanhNB | Done | Done
16 | Create a promotion | KhanhNB | Done | Done
17 | Remove promotion | KhanhNB | Done | Done
18 | View order list that need to be processed | TienPV | Done | Done
19 | Process an order (Approve/Reject) | TienPV | Done | Done
20 | Update personal phone number | SyTT | Done | Done
21 | Update personal address | SyTT | Done | Done
22 | Update personal name | SyTT | Done | Done

## Iter2
# | Screen / Function | In Charge | Status | Notes
1 | Create reports to send to admin (Landlord + Tenant) | SyTT | Done
2 | Create a rental order | SyTT | Done
3 | View tenant information | SyTT | Done
4 | Update points to personal account | ThangHQ | Done
5 | Ban account | ThangHQ | Done | Admin can opt to ban users for various predefined duration (100, 200, 365 or permanent) - User has been banned cannot log in after that
6 | View personal point transaction history | ThangHQ | Done
7 | Create a new post about a house for rent | TienPV | Done
8 | View all personal landlord post | TienPV | Done
9 | Create a transaction on personal posting | TienPV | Done | Pay for post - Landlord can see their current balance before proceeding to payment - Logic: select a post to make payment - Substract balanace after payment, add to database transaction history - Promotion
10 | Process report | AnhNT | Done
11 | Remove post | AnhNT | Done | Edit post's status by admin - Status of a post will be "Deleted" after delete
12 | Add account | TungDT | Done
13 | Edit account | TungDT | Done
14 | Disable account | TungDT | Done
15 | Vote for room | KhanhNB | Done
16 | Comment for room | KhanhNB | Done
17 | Upload User's Avatar | AnhNT | Done | Done
18 | Pagination | AnhNT | Done
19 | Update duration of promotion | KhanhNB | Done

## Iter3
# | Screen / Function | In Charge | Status | Notes
1 | Login | ThangHQ | Done | Re-send confirmation email for user
2 | Forgot password | ThangHQ | Done | Modify behavior of forgot password function
3 | Testing | ThangHQ, TienPV, KhanhNB, TungDT, AnhNT, SyTT | Done | Independence testing functionalities
4 | Search Post | AnhNT | Done | Fix bugs in search
5 | View promotion | KhanhNB | Done | Update new UI for promotion